## Slide 1
Inter-Task project ‘Synergies of green hydrogen and bio-based value chains deployment’ (T39 T6)
Task 39 Business Meeting
Online| February 23, 2023
Franziska Müller-Langer, DBFZ

## Slide 2
Work Packages
T39
T39
T39
T39 project team
Franziska Müller-Langer (DE), Glaucia Souza (BR), Dina Bacovsky (AT), Tomas Ekbom (SE), Luiz Augusto Horta Nogueira (BR), Rubens Maciel (BR), Nicolaus Dahmen (DE); Marco Buffi (EC), Steve Rogers (AUS), Paul Benett (NZ)

## Slide 3
From June 2022 to November 2024 (30 months)
Initial plan: From Jan 2022 to June 2024 (30 months)
Timeline
Kick-off meeting
June 2022
First expert
workshop in Oct 2022
Work package / Project month | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22 | 24 | 26 | 28 | 30
WP 1 ¦ Status quo of synergy value chains |  |  | X |  | R1 |  |  |  |  |  |  |  |  |  | 
WP 2 ¦ Case Studies on hydrogen from biomass |  |  |  |  |  |  |  |  |  |  | R2 | W1 |  |  | 
WP 3 ¦ Case Studies on hydrogen use in bio-based processes |  |  |  |  |  |  |  |  |  |  | R2 | W1 |  |  | 
WP 4 ¦ Synergies and services from hydrogen and bio-based value chains deployment |  |  |  |  | X |  |  |  |  |  |  |  |  | R3 | W2
WP 5 ¦ Assessment and Synthesis |  |  |  |  |  |  |  |  |  |  |  |  |  | R3 | W2
WP 6 ¦ Project management and dissemination |  |  | PS |  |  | PS |  |  | PS |  |  | PS |  |  | PS
x is workshop (either internal or with externals) R is report W is webinar PS is project status to ExCo |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Note:
WP 1+x Workshop proposed for end of March 2023 in Berlin

## Slide 4
After ExCo88 in 04/2022
Task contribution 232.000 USD
ExCo funding 70.000 USD
Total budget 302.000 USD
Pending confirmation of budget allocation from T39 25.000 USD
T39 internal
Budget allocation within T39 contributors
DE: T39 coordinator, WP1,2,3,5: 14.500 USD
BR: WP1,2,5: 10.500 USD
Further contribution inkind
Budget
T39
 |  | Participating Task: Cost/Budget (USD) |  |  |  |  |  |  |  |  |  | 
WP | Activity | 32 | 33 | 34 | 36 | 37 | 39 *) | 40 | 42 | 44 | 45 | Sub-total
1 | Status quo of synergy value chains | 2500 | 2500 | 2500 | 2500 | 5000 | 2500 | 15000 | 1000 | 2500 | 2500 | 38500
2 | Case Studies on hydrogen from biomass | - | 15250 | - | 17250 | - | 8000 | - | - | 5000 | 2500 | 48000
3 | Case Studies on hydrogen use in bio-based processes | 11000 | 3000 | 21000 | - | 13500 | 12000 | 3000 | 13000 | 5000 | 2500 | 84000
4 | Synergies and services from hydrogen and bio-based value chains deployment | - | - | - | - | 16000 | - | 15000 | - | 16000 | - | 47000
5 | Assessment and Synthesis | 1500 | 1500 | 1500 | 1500 | 4375 | 2500 | 5875 | 1000 | 3375 | 31375 | 54500
6 | Project management and dissemination | - | - | - | - | - | - | - | - | 30000 | - | 30000
Total Cost/Budget |  | 15000 | 22250 | 25000 | 21250 | 38875 | 25000 | 38875 | 15000 | 61875 | 38875 | 302000
From Task budget |  | 12000 | 18000 | 20000 | 17000 | 30000 | 20000 | 30000 | 12000 | 43000 | 30000 | 232000
From ExCo Strategic Fund |  | 3000 | 4250 | 5000 | 4250 | 8875 | 5000 | 8875 | 3000 | 18875 | 8875 | 70000
*) estimated budget; confirmation later |  |  |  |  |  |  |  |  |  |  |  | 
Notes: 10 participating Tasks

## Slide 5
WPs T39 contribution
WP 2 & 3 | Work in progress
Report “Renewable hydrogen and bioenergy: prospects in Brazil” (Glaucia, Rubens, Luiz, Heitor):
  Considered cases:
  Hydrogen from ethanol reforming
  Electric vehicles with hydrogen fuel cells generated by reforming ethanol on-board
  Production of green ammonia using hydrogen produced by reforming biomethane generated in the biodigestion of ethanol vinasse
  Production of HVO and SAF with renewable hydrogen
Work on initial list of case studies for WP 3 (Franziska with Glaucia, Marco, Nico):
  Considered cases:
  Pilot-SBG >> renewable methane/LNG
  PTG-HEFA >> HEFA SPK
  refuels >> Green refineries with focus on fuel production
  Omega Green >> hydrogen in HVO plants
  Further case studies from Australia and IEA AMF >> we can decide to include them later.

## Slide 6
WPs T39 contribution
WP 2 & 3 | Work in progress

## Slide 7
Contact
Dr.-Ing. Franziska Müller-Langer
Head of Department Biorefineries franziska.mueller-langer@dbfz.de | +49 341 2434 423